## Version Control
`
Version Control of this Change Plan and Schedule
Notes to Change Requester: 1) This is to document the version control of this plan and capture what have been revised since the initial version.
Date | Version | Prepared by (Name of Change Requester) | Description | Endorsed By (Name of Change Preparation Manager)
2020-08-10 | 1 | Aromal Raj | Filebeat installation | Jeff Kung

## Mapping (hidden)
Impact or Severity rating
Likelihood | 1 - Negligible | 2 - Minor | 3 - Moderate | 4 - Major | 5 - Catastrophic | Note that the initial 5x5 matrix has been used, but that : (a) the 1-5 likelihood scale is unchanged, (b) the initial 1-5 Impact scale has been re-mapped to be on a 1-4 scale, and the direction reversed.
5 - Almost Certain | Low | Moderate | High | Ultra | Ultra
4 - Likely | Low | Moderate | High | Ultra | Ultra
3 - Possible | Low | Low | Moderate | High | Ultra
2 - Unlikely | Insignificant | Low | Low | Moderate | High
1 - Rare | Insignificant | Insignificant | Low | Moderate | High
|  |  |  | Risk Level | Risk Rating | Urgency of Action
|  |  |  | 5 | Ultra | Immediate attention is required. Do not proceed until risk is mitigated appropriately.
|  |  |  | 4 | High | There are significant risk(s) that require immediate attention.
|  |  |  | 3 | Moderate | There are significant risk(s) that require appropriate mitigation and monitoring.
|  |  |  | 2 | Low | Risks are considered as not significant. Appropriate mitigation and monitoring required.
|  |  |  | 1 | Insignificant | Risks are considered to be insignificant. No mitigation required.
Current change type |  | Low (Default) | Likelihood |  |  | High
|  | 1 | 2 | 3 | 4 | 5
Adjusted Impact rating 1-4 | 4 - Minor/Localized | Minor | Minor | Minor | Minor | Minor
| 3 - Moderate/Limited | Minor | Minor | Minor | Minor | Major
| 2 - Significant/Large | Major | Major | Major | Major | Major
| 1 - Extensive/Widespread | Major | Major | Major | Major | Major
|  | Low (Default) | Likelihood |  |  | High
Select Major or Minor change type(from list) |  | 1 | 2 | 3 | 4 | 5
Adjusted Impact rating 1-4 | 4 - Minor/Localized | Minor | Minor | Minor | Minor | Major
NOTE : The cell contents are used to set the Major or Minor; make sure to spell correctly | 3 - Moderate/Limited | Minor | Minor | Minor | Major | Major
| 2 - Significant/Large | Major | Major | Major | Major | Major
| 1 - Extensive/Widespread | Major | Major | Major | Major | Major
|  | Low (Default) | Likelihood |  |  | High
Select Risk level 1-5 (5 as highest) |  | 1 | 2 | 3 | 4 | 5
Adjusted Impact rating 1-4 | 4 - Minor/Localized | 1 | 1 | 2 | 2 | 2
| 3 - Moderate/Limited | 1 | 2 | 2 | 3 | 3
| 2 - Significant/Large | 2 | 2 | 3 | 4 | 4
| 1 - Extensive/Widespread | 4 | 4 | 5 | 5 | 5
Note on D35: Warning message. Do not use !!!
Note on C42: For warning message. Do not use !!!

## Impact-Risk Assessment (Prod)
| Change Impact & Risk assessment | Required entry
| (answer questions, note Impact & Risk ratings ; save file - named accordingly | Derived content
| 2020-08-10 18:03 | June 23, 2011 v0.7 |  |  |  | Unweighted points |  |  | Weighted points
[5 empty] | Weight | Points | Points | Points | Points | Points | Points | Maximum score | Picklist strings for questions
# | Impact assessment-related Questions | Pick from the list offered for each row | Selected list item code | Contribution added | [8 empty] | String for 1 | String for 2 | String for 3 | [7 empty] | In this section, click the cell next to the question and select one of the answers
1 | Are you introducing a new systems/technology with this change? | No | 1 | 0 | 4 | 0 | 5 | 10 | 0 | 20 | 40 | 40 | No | Yes - not Lifeblood/Critical | Yes - Lifeblood/Critical | [7 empty] | No | Yes - not Lifeblood/Critical | Yes - Lifeblood/Critical
2 | What is the impact on related Systems/Applications during this change? | None | #N/A | #N/A | 5 | 0 | 5 | 10 | 0 | 25 | 50 | 50 | No Impact | Performance Degradion | Full / Partial Outage | [7 empty] | No Impact | Performance Degradion | Full / Partial Outage
3 | How many related Systems/Applications will be impacted? | Single application | #N/A | #N/A | 4 | 0 | 4 | 10 | 0 | 16 | 40 | 40 | Only one | Multiple - Less then Five | Mulitple - More then Five | [7 empty] | Only one | Multiple - Less then Five | Mulitple - More then Five
4 | Has the planned implementation been done before in CPA IT Environment? | More than 10 times | 1 | 0 | 4 | 0 | 4 | 10 | 0 | 16 | 40 | 40 | More than 10 times | Up to 10 times | No | [7 empty] | More than 10 times | Up to 10 times | No
5 | Are staff / business user or public customer impacted during the change window? | None | 1 | 0 | 4 | 0 | 4 | 10 | 0 | 16 | 40 | 40 | None | Yes - inside maintenance window | Yes - outside maintenance window | [7 empty] | None | Yes - inside maintenance window | Yes - outside maintenance window
6 | Is the plan for Fallback/ Contingency / Remediation tested & proven? | Yes - and proven | 1 | 0 | 3 | 0 | 4 | 10 | 0 | 12 | 30 | 30 | Yes - and proven | Yes - but not proven | No | [7 empty] | Yes - and proven | Yes - but not proven | No
7 | Is there a single point of failure during implementation ? | No | 1 | 0 | 2 | 0 | 4 |  | 0 | 8 |  | 8 | No | Yes | [8 empty] | No | Yes
8 | Is the implementation within peak business hours (9am - 6pm Monday - Friday)? | Yes | 2 | 8 | 2 | 0 | 4 |  | 0 | 8 |  | 8 | No | Yes | [8 empty] | No | Yes
|  |  | TOTAL SCORE | #N/A | [7 empty] | 256
| Assessed Likelihood of Impact if the change does not work (5 as highest likelihood) | 1 - Rare(<2.5%) |  |  | Derived Impact Rating 1 to 4 | #N/A | [16 empty] | Pick the scale of number 5, 5 is the highest likelihood that the change will fail
[13 empty] | Impact | Adjusted scaled rating | Available ? | Impact level | Approvals required from | Impact range lower end % of maximum | Impact range % of maximum | Impact range lower end score | Impact range upper end score | Which one ?
Impact rating (1 as highest): | #N/A | [11 empty] | 1 | 5 | Yes | Extensive / Widespread | Team Lead(s) ; Assessor(s) ; Technical Support Mgr ; Service Operations Mgr ; CAB forum | 45 | 100 | 115.2 | 256 | #N/A | Impact is the impact to the existing environment. 1 mean will affect life blood
| #N/A |  |  |  | 1 | Insignificant | [6 empty] | 2 | 3 | Yes | Significant / Large | Team Lead(s) ; Assessor(s) ; CAB forum | 30 | 45 | 76.8 | 115.2 | #N/A
Risk Level rating (5 as highest) : | Risk Level 1 |  |  |  | MINOR | [7 empty] | 3 | 2 | Yes | Moderate / Limited | Team Lead(s) ; Assessor(s) ; CAB forum | 20 | 30 | 51.2 | 76.8 | #N/A | Risk means the chance that this change will create high severity problem
| ^---------- Enter this detail into the applicable Remedy Change record | [11 empty] | 4 | 1 | Yes | Minor / Localized | Team Lead(s) ; Assessor(s) | 0 | 20 | 0 | 51.2 | #N/A
Note on C5: For each row, the level of impact rises through the choices.
Note on E14: Only displayed if all questions have been answered
Note on A15: Warning message. Do not use !!!
Note on B15: Pick from the 1 to 5 scale
Note on T16: The lower limit comes from the upper limit of the preceding (lower)level.
Note on B18: Warning message Do not use !!!
Note on F18: Assessed Risk level picked off relevant Mapping table. Do NOT use !!!
Note on G18: Risk label, according to the derived risk level.
Note on F19: Assessed Change type - Major or Minor picked off relevant Mapping table.. Folded to UPPERCASE. Do NOT use !!!
Note on B20: Warning message. Do not use !!!
Note on C21: Assessed Change type - Major or Minor picked off relevant Mapping table.. Folded to UPPERCASE. Do NOT use !!!

## Impact-Risk Assessment (ETE)
| Change Impact & Risk assessment | Required entry
| (answer questions, note Impact & Risk ratings ; save file - named accordingly | Derived content
| 2020-08-10 18:03 |  |  |  |  | Unweighted points |  |  | Weighted points
[5 empty] | Weight | Points | Points | Points | Points | Points | Points | Maximum score | Picklist strings for questions
# | Impact assessment-related Questions | Pick from the list offered for each row | Selected list item code | Contribution added | [8 empty] | String for 1 | String for 2 | String for 3 | [7 empty] | In this section, click the cell next to the question and select one of the answers
1 | Are new systems/technology involved ? | No | 1 | 0 | 4 | 0 | 5 | 10 | 0 | 20 | 40 | 40 | No | Yes - not Lifeblood/Critical | Yes - Lifeblood/Critical | [7 empty] | No | Yes - not Lifeblood/Critical | Yes - Lifeblood/Critical
2 | Level of Business Impacts on Systems/Applications (in case of worst scenario)? | None | 1 | 0 | 5 | 0 | 5 | 10 | 0 | 25 | 50 | 50 | None | Intermediate | Significant or above | [7 empty] | None | Intermediate | Significant or above
3 | How many System/Application will be affected ? | Single application | 1 | 0 | 4 | 0 | 10 |  | 0 | 40 |  | 40 | Single application | Multiple applications | [8 empty] | Single application | Multiple applications
4 | Has this implementation been done before ? | More than 10 times | 1 | 0 | 4 | 0 | 4 | 10 | 0 | 16 | 40 | 40 | More than 10 times | Up to 10 times | No | [7 empty] | More than 10 times | Up to 10 times | No
5 | Is there a service outage during the implementation ? | None | 1 | 0 | 4 | 0 | 4 | 10 | 0 | 16 | 40 | 40 | None | Yes - inside maintenance window | Yes - outside maintenance window | [7 empty] | None | Yes - inside maintenance window | Yes - outside maintenance window
6 | Is a plan for Fallback/ Contingency / Remediation in place ? | Yes - and proven | 1 | 0 | 3 | 0 | 4 | 10 | 0 | 12 | 30 | 30 | Yes - and proven | Yes - but not proven | No | [7 empty] | Yes - and proven | Yes - but not proven | No
7 | Is there a single point of failure during implementation ? | No | 1 | 0 | 2 | 0 | 4 |  | 0 | 8 |  | 8 | No | Yes | [8 empty] | No | Yes
8 | Is the implementation within office hours ? | Yes | 2 | 8 | 2 | 0 | 4 |  | 0 | 8 |  | 8 | No | Yes | [8 empty] | No | Yes
|  |  | TOTAL SCORE | 8 | [7 empty] | 256
| Assessed Likelihood of Impact if the change does not work (5 as highest likelihood) | 1 - Rare(<2.5%) |  |  | Derived Impact Rating 1 to 4 | 4 | [16 empty] | Pick the scale of number 5, 5 is the highest likelihood that the change will fail
[13 empty] | Impact | Adjusted scaled rating | Available ? | Impact level | Approvals required from | Impact range lower end % of maximum | Impact range % of maximum | Impact range lower end score | Impact range upper end score | Which one ?
Impact rating (1 as highest): | 4 - Minor/Localized | Minor | [10 empty] | 1 | 5 | Yes | Extensive / Widespread | Team Lead(s) ; Assessor(s) ; Technical Support Mgr ; Service Operations Mgr ; CAB forum | 45 | 100 | 115.2 | 256 |  | Impact is the impact to the existing environment. 1 mean will affect life blood
| ^---------- Enter this detail into the applicable Remedy Change record |  |  |  | 1 | Insignificant | [6 empty] | 2 | 3 | Yes | Significant / Large | Team Lead(s) ; Assessor(s) ; CAB forum | 30 | 45 | 76.8 | 115.2
Risk Level rating (5 as highest) : | Risk Level 1 |  |  |  | MINOR | [7 empty] | 3 | 2 | Yes | Moderate / Limited | Team Lead(s) ; Assessor(s) ; CAB forum | 20 | 30 | 51.2 | 76.8 |  | Risk means the chance that this change will create high severity problem
| ^---------- Enter this detail into the applicable Remedy Change record | [11 empty] | 4 | 1 | Yes | Minor / Localized | Team Lead(s) ; Assessor(s) | 0 | 20 | 0 | 51.2 | X
Note on C5: For each row, the level of impact rises through the choices.
Note on E14: Only displayed if all questions have been answered
Note on A15: Warning message. Do not use !!!
Note on B15: Pick from the 1 to 5 scale
Note on T16: The lower limit comes from the upper limit of the preceding (lower)level.
Note on B18: Warning message Do not use !!!
Note on F18: Assessed Risk level picked off relevant Mapping table. Do NOT use !!!
Note on G18: Risk label, according to the derived risk level.
Note on F19: Assessed Change type - Major or Minor picked off relevant Mapping table.. Folded to UPPERCASE. Do NOT use !!!
Note on B20: Warning message. Do not use !!!
Note on C21: Assessed Change type - Major or Minor picked off relevant Mapping table.. Folded to UPPERCASE. Do NOT use !!!

## Pre-Approval Questions
Filebeat installation
Pre-Approval Questions | Feedback from requestor
For Database (Oracle) changes:
1. If you have insert/update/delete SQLs, have you put down the expected SQL counts after insert/update/delete SQL execution for verification purpose? Have you prepared the backup scripts to remove the newly inserted records or recover the original records in case a fallback is required? | N/A
N/A
2. For table structure alter, please confirm that there is no impact to the application while applying “ALTER TABLE” statement online if it’s necessary to do so. As you know, the database system will temporarily lock the table during altering and any DDL SQL referring to that table will be on hold and wait until it’s completed.
3. If you have new tables created: | N/A
· Have you prepared script for creating synonyms and granting privileges to application database users?
· Have you prepared the fallback scripts for these tables including synonyms and revoking privileges granted?
· Will there be SQL scripts of creating their indexes for performance purpose?
· What’s the initial size and growth trend of these new tables and their indexes?
· Is the server having enough disk space for new tables? Please check with SAO operation management.
· Do you need to housekeep of these tables? If no, please explain why? If yes, how and please provide the schedule. Do you need to archive before housekeeping of these tables and why?
· Do you need to gather table statistics regularly to optimize the execution plans? If yes, how and please provide the schedule.
4. If you need to create/replace views: | N/A
· Have you prepared script for creating synonyms and grant privileges for new views?
· Have you prepared the fallback scripts for these views including their synonyms and revoking privileges granted?
5. If you have materialized view (either remote or local) created, does the refresh schedule defined, if yes, what is the schedule? How long does the refresh expected to be completed? Is it an atomic refresh? What is the impact if the refresh failed during deployment and afterward? | N/A
6. If you have package definition changes, they may invalidate schema objects which will be revalidated by on-demand automatic recompilation, but please recompile invalid objects in advance of user calls because it may take an unacceptable time to complete to impact system performance especially where complex dependencies are employed. | N/A
7. If you have database link defined, is there any other alternative? As you know, it is difficult to maintain if databases are interconnected by database links. What is the expected result when the remote database is not available? Does the application handle the exception when remote database is not available? Have you prepared tnsnames definition referred by database production in production environment. | N/A
8. If you have new partition to be added, please state the housekeeping and archiving policy as partitioned tables are normally large tables. | N/A
For Middleware (VAP/WAS) changes:
1. Have you turned off unnecessary development debug option in the deployment object? | N/A
2. Has the change incurred change in JVM Heap Usage? If yes, have you made the request to enlarge the Java Heap to avoid out of memory? Is the WAS server having enough resource to cater this additional utilization? | N/A
3. Do you need to deploy new JVM in existing production servers? If yes, have you submitted the application profile to HP BAU support team to perform impact analysis? Have you received the positive result to allow this new JVM setup in existing servers to ensure enough resource to cater this requirement? | N/A
4. Is it necessary to restart deployment manager to make this change effective? If yes, have you instructed HP BAU support to do so? | N/A
5. If you have both VAP and WAS changes, please confirm the execution sequence of VAP and WAS changes having no impact to online service during the production implementation. | N/A
For Data Cloning from Production:
1. Do you need data masking for this data retrieval from Production due to sensitive data included? If yes, has the application owner already approved this data retrieval with masking requirement? | N/A
2. Do you know if this data retrieval is going to be directly performed in the production system while it’s still available to end-users? If yes, will it have any impact on the performance? If it has impact, have you informed the application owner about this activity on the tentative date/time during the data retrieval? | N/A
For Read-only Access in Production Database:
1. Describe how you can access this Production database directly. If using Oracle connect tool, please provide sql*net connection and user account information. | N/A
2. Show the major SQL statements you are going to execute after connecting to the database and please estimate the SQL record counts if possible. | N/A
3. Provide the tentative start date & time and end date & time of this activity. | N/A

## Milestones
Filebeat installation
Milestones
Notes to Change Requester: 1) This section should be used to capture the major milestones and phases throughout the change implementation 2) For typical changes, there should be at least 3 phases, namely pre-implementation verification, implementation and post-implementation verification.
# | Major Milestones | Business Impact | Implementation Start Time (HKT) | Implementation End Time (HKT )
1 | Preparation / Pre-implement Verification Tasks | No Impact | 2020-08-14 10:00 | 2020-08-14 10:30
2 | Implementaion | No Impact | 2020-08-14 10:30 | 2020-08-14 11:30
3 | Post-Impln Verification | No Impact | 2020-08-14 11:30 | 2020-08-14 13:30
4 | Fallback or Contingency or Recovery Steps | No Impact | 2020-08-14 13:30 | 2020-08-14 14:35
5
6
7
8

## Pre-impln Verification
Filebeat installation
Preparation Tasks/Pre-Implementation Verification Procedures
Notes to Change Requester: 1) It aims to make sure all the pre-requisites have been met before the actual change implementation, it typically includes: • verify if the impacted system(s) is/are stable and running smoothly • verify if the software media and hardware equipment / parts to be used during the change implementation is functioning, error free and virus free • ensure required system data backup is completed and ready to cater for any remediation procedures • turn on system trace/log to collect diagnostic information in case of any abnormalities • ensure system monitoring and alerts are in place to monitor system healthiness during/after the change • baseline the performance and capacity metrics of the impacted system(s) so as to facilitate subsequent comparisons • re-confirm with corresponding stakeholders regarding the change should be proceeded as planned • inform corresponding stakeholders and support organizations that the change is about to start 2) If any preparation or pre-implementation step fails, the Change Implementaton Manager should make a call regarding whether to cancel the change.
# | Preparation / Pre-implement Verification Tasks | Start Time | End Time | Duration (mins) | Action By (Team/Name) | Expected Result | Follow-up action if the expected result is negative | Remarks
1 | Check Servers
1.1 | Check the following hosts are registered in AWX or not. Register them if not listed. HKGX3LAP0079.cpadm001.corp.cathaypacific.com, HKGX3LAP0088.cpadm001.corp.cathaypacific.com, HKGX3LAP0089.cpadm001.corp.cathaypacific.com, HKGX4LAP0088.cpadm001.corp.cathaypacific.com, HKGX3LAP0080.cpadm001.corp.cathaypacific.com, HKGX3LAP0081.cpadm001.corp.cathaypacific.com, HKGX3LAP0082.cpadm001.corp.cathaypacific.com, HKGX3LAP0083.cpadm001.corp.cathaypacific.com, HKGX4LAP0064.cpadm001.corp.cathaypacific.com, HKGX4LAP0065.cpadm001.corp.cathaypacific.com, HKGX4LAP0066.cpadm001.corp.cathaypacific.com, HKGX4LAP0067.cpadm001.corp.cathaypacific.com, HKGX3LJB0003.cpadm001.corp.cathaypacific.com, HKGX3LJB0004.cpadm001.corp.cathaypacific.com, HKGX4LJB0003.cpadm001.corp.cathaypacific.com, HKGX4LJB0004.cpadm001.corp.cathaypacific.com | 2020-08-14 10:00 | 2020-08-14 10:30 | 30 | CPA DC Infra Team / TBC

## Implementation Procedures
Filebeat installation
Implementation Procedures (may not be applicable for preliminary change)
Notes to Change Requester: 1) The implementation procedures should cover ALL the steps that are to be carried out in this change, either by single party or multiple parties. If some of steps are documented in a separate document, the linkage to those steps should be clearly indicated here and the document should be attached together with this change plan and schedule. 2) The activities or implementation steps that have dependencies must be clearly identified
# | Implementation Steps | Start Time | End Time | Duration (Mins) | Action By (Team/Name) | Dependencies | Remarks
1 | Install beats via Ansible AWX
1.1 | Run ansible playbook to install filebeat to the following servers: HKGX3LAP0079.cpadm001.corp.cathaypacific.com, HKGX3LAP0088.cpadm001.corp.cathaypacific.com, HKGX3LAP0089.cpadm001.corp.cathaypacific.com, HKGX4LAP0088.cpadm001.corp.cathaypacific.com, HKGX3LAP0080.cpadm001.corp.cathaypacific.com, HKGX3LAP0081.cpadm001.corp.cathaypacific.com, HKGX3LAP0082.cpadm001.corp.cathaypacific.com, HKGX3LAP0083.cpadm001.corp.cathaypacific.com, HKGX4LAP0064.cpadm001.corp.cathaypacific.com, HKGX4LAP0065.cpadm001.corp.cathaypacific.com, HKGX4LAP0066.cpadm001.corp.cathaypacific.com, HKGX4LAP0067.cpadm001.corp.cathaypacific.com, HKGX3LJB0003.cpadm001.corp.cathaypacific.com, HKGX3LJB0004.cpadm001.corp.cathaypacific.com, HKGX4LJB0003.cpadm001.corp.cathaypacific.com, HKGX4LJB0004.cpadm001.corp.cathaypacific.com | 2020-08-14 10:30 | 2020-08-14 11:30 | 60 | CPA DC Infra Team / TBC
Formulas:
End Time = [Start Time]+TIME(0,[Duration (Mins)],0)

## Post-impln Verification
Filebeat installation
Post-implement Verification Procedures
Notes to Change Requester: 1) The verification procedures should include steps to make sure the change is effective and it does not affect other components/functionality/etc. 2) The expected result must be clearly provided. 3) The acceptance criteria should be explicitly listed in below how this change is confirmed to be a sucessful implementation. 4) State explicitly the verification parties in Action By (Team/Name): DXC verifier (not DXC implementer), IM verifier and BU verifier.
# | Acceptance Criteria |  |  |  | Observation period and tasks to be done
1 | Check installed beat |  |  |  | #1, 120 mins
# | Post-implement Verification Tasks | Start Time | End Time | Duration (Mins) | Action By (Team/Name) | Expected Result | Follow-up action if the verification result is not positive | Remarks
1 | Check installed beats
1.1 | Login servers and run "rpm -qa ¦ grep beat" | 2020-08-14 11:30 | 2020-08-14 13:30 | 120 | CPA DC Infra Team / TBC | filebeat should be found in corresponding servers. Filebeat: HKGX3LAP0079.cpadm001.corp.cathaypacific.com, HKGX3LAP0088.cpadm001.corp.cathaypacific.com, HKGX3LAP0089.cpadm001.corp.cathaypacific.com, HKGX4LAP0088.cpadm001.corp.cathaypacific.com, HKGX3LAP0080.cpadm001.corp.cathaypacific.com, HKGX3LAP0081.cpadm001.corp.cathaypacific.com, HKGX3LAP0082.cpadm001.corp.cathaypacific.com, HKGX3LAP0083.cpadm001.corp.cathaypacific.com, HKGX4LAP0064.cpadm001.corp.cathaypacific.com, HKGX4LAP0065.cpadm001.corp.cathaypacific.com, HKGX4LAP0066.cpadm001.corp.cathaypacific.com, HKGX4LAP0067.cpadm001.corp.cathaypacific.com, HKGX3LJB0003.cpadm001.corp.cathaypacific.com, HKGX3LJB0004.cpadm001.corp.cathaypacific.com, HKGX4LJB0003.cpadm001.corp.cathaypacific.com, HKGX4LJB0004.cpadm001.corp.cathaypacific.com | Report playbook issue to Implement manager.
Formulas:
End Time = [Start Time]+TIME(0,[Duration (Mins)],0)

## Remediation Procedures
Filebeat installation
Remediation Procedures (including fallback, contingency or recovery)
Notes to Change Requester: 1) For each possible failure scenarios, there must be corresponding remediation procedures. 2) The observation period and 'point of no return' should be pre-agreed and clearly stated. 3) Sometimes fallback is not feasible at the time or after some time when the change has been implemented in production, then contingency/recovery plan and actions must be provided in this section. 4) Please list out all proven sets of remediation plans against various change failure scenario.
# | Scenario |  |  |  | Steps to be executed | To be activated
1 | Any issue occur during implemetation |  |  |  | step 1
# | Fallback or Contingency or Recovery Steps | Start Time | End Time | Duration (mins) | Action By (Team/Name) | Business Impact
1 | Any issue occur during implemetation
1.1 | fallback all the configuration done in implementation tab | 2020-08-14 13:30 | 2020-08-14 14:30 | 60 | CPA DC Infra Team / TBC
1.2 | Inform SQM team | 2020-08-14 14:30 | 2020-08-14 14:35 | 5 | CPA SQM Team / Wilson Chow
Formulas:
Start Time = [End Time, row above]
End Time = [Start Time]+TIME(0,[Duration (mins)],0)

## Contacts
Filebeat installation
Contact List
Role | Team | Name | Contact Number | Location
Requester | CPA SQM Team | Polly Lam | 9669 0746 | 6/F Cathay City
Implementation Manager | CPA DC Infra Team | Billy Tam | 9378 8562 | 6/F Cathay City
Implementor | CPA DC Infra Team | TBC | 9225 5764 | 6/F Cathay City
Verifier | CPA SQM Team | Wilson Chow | 9669 0746 | 6/F Cathay City
Date/Time | Team | Team/Name | Contact Number | Remarks
Conference Bridge Number
Location | Number | Remarks | Remarks
HKG
SYD
AUS
PIN

## Supplement Info
Filebeat installation
| Supplement Forms Attached | 1
2
3
4
5
6
7
8
9
10

## Source & Build Info
Filebeat installation
Source & Build Information
Notes to Change Requester: 1) The verification procedures should include steps to make sure the change is effective and it does not affect other components/functionality/etc. 2) The expected result must be clearly provided. 3) The acceptance criteria should be explicitly listed in below how this change is confirmed to be a sucessful implementation.
1) The source control repository path can be referred to the application inventory (Column AD). http://team.cathaypacific.com/sites/imt/saopublic/configmgmt/Configuration%20Repository/Application_Inventory.xlsx
2) The application for change and release must be under source control unless it is exempted (refer to application inventory)
3) The standard practices of branching and tagging should be referred to Proposed Source Version Control Structure and Practices v1.0 http://team.cathaypacific.com/sites/imt/saopublic/configmgmt/Source%20Code%20Control/Proposed%20Source%20Version%20Control%20Structure%20and%20Practices%20v1.0.doc
4) Developer and build personnel are in different roles and should NOT be the same person unless there is an Email approval from CX SA or above. (Refer to the Application Release Build and Deployment process: http://team.cathaypacific.com/sites/imt/saopublic/configmgmt/Source%20Code%20Control/Application%20Release%20Build%20and%20Deployment%20v1.0.doc)
5) The guidelines for checksum generation and verification can be referred to Guidelines for Generation and Verification of MD5 Checksum. http://team.cathaypacific.com/sites/imt/saopublic/configmgmt/Source%20Code%20Control/Guidelines%20for%20Generation%20and%20Verification%20of%20MD5%20Checksum%20v1.0.docx
6) All package build must reside in the Definitive Media Library. Location: //CLKLXCVSP01/pre-authorized/application/version/environment/ Example: //CLKLXCVSP01/pre-authorized/1029 – Flight Monitor Sample/2.0.5/ETE 001/bin/ For more information on DML see: http://team.cathaypacific.com/sites/imt/saopublic/relmgmt/Shared%20Documents/SAO_DML%20Overview.pptx
Within Source Version Control (Refer to application inventory - point 1) If yes, the following "Source Version control Information" need to be filled | : | (Yes/No)
I) Source Version Control Information
Application Version (optional) | :
CVS/Subversion Repository Path | :
Source Code Branch Name | :
Source Code Tagging Name | :
II) Release Build Information
NOTE: You are required to provide the following information for each build. Create additional sections as required.
Release Build Description (e.g., Build 1 for SIT) | :
Release Version | :
Release Build Prepared By | :
Release Build Date | :
Release Build Location (Specify location in DML) | :
Release Items' Checksum Attachment (txt file) | :
(including release items and corresponding MD5 checksum into DML build location)
Note on A19: Tagging Syntax: ID – app code–app version–status–date

## Documents updated
Filebeat installation
| List of documents updated | 1
2
3
4
5
6
7
8
9
10

## Document Control
Document Control of X34.7 Change Plan and Schedule Template
Notes to Change Requester: 1) This is the document control of the template. Change Requester is not required to fill anything to this tab.
Date | Version | Effective Date | Prepared / Updated by | Changed Details | Endorsed By
2009-12-29 | 1 | 2009-12-29 | Chris Chan | First version | YC Chan
2010-01-19 | 1.1 | 2010-01-19 | Dilys Kwok | Revised date format | YC Chan
2010-02-03 | 1.2 | 2010-02-03 | Dilys Kwok | 1. Amended the wordings from 'implementation/fallback/verification details' to 'implementation/fallback/verification procedures'. 2. Added instructions and examples in Verification Procedures 3. Added a tab for input of documents list to be updated related to the change implementation. | YC Chan
2010-09-24 | 1.3 | 2010-09-24 | Dilys Kwok | 1. Provided more detailed notes to guide change requester to fill out the form 2. Added 'Pre-impln Verfication' tab 3. Renamed 'Verification Procedures' tab to 'Post-impln Verification' 4. Merged Fallback Scenario tab with Fallback Procedures tab and rename it to 'Remediation Procedures | YC Chan
2011-10-19 | 2 | 2011-10-24 | Stephen Woo | Add the Impact-Risk Assessment page to assist requestor to classify minor/major change | Yin Tam
2011-12-16 | 3 | 2011-12-16 | Stephen Woo | Add the Source & Build Info page to comply with Internal Audit requirements for Application Release build and deployment control | Yin Tam
2012-11-05 | 3.1 | 2012-11-15 | Keith Yeung | Add build related information to Source & Build to accommodate deployment process
2012-11-08 | 3.2 | 2012-12-01 | Alvis Cheng | Include Request for Change tab to replace obsolete Technical Service Request
2013-04-02 | 3.3 | 2013-04-09 | Harri Chong | Include 2 new questions in Pre-approval tab | Yin Tam
2013-05-24 | 3.4 | 2013-05-24 | Harri Chong | Include Data Cloning and Read-only Access in Pre-approval tab | Yin Tam
2013-06-27 | 3..5 | 2013-07-03 | YC Chan | Include HP, IM and BU verifier explicitly in Change Plan | Yin Tam